## Industry pages (5)
# | Industry page (prune) | 301 redirect to pillar | Action | Status (24 Aug 2026)
1 | https://finanshels.com/services/accounting-firm-for-ecommerce-in-uae | https://finanshels.com/bookkeeping-services-uae | 301 redirect to pillar, then unpublish the page | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
2 | https://finanshels.com/services/accounting-firm-for-restaurants-in-uae | https://finanshels.com/bookkeeping-services-uae | 301 redirect to pillar, then unpublish the page | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
3 | https://finanshels.com/services/accounting-firm-for-smes-in-uae | https://finanshels.com/bookkeeping-services-uae | 301 redirect to pillar, then unpublish the page | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
4 | https://finanshels.com/services/accounting-firm-for-startups-in-uae | https://finanshels.com/bookkeeping-services-uae | 301 redirect to pillar, then unpublish the page | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
5 | https://finanshels.com/services/hire-an-accountant-in-uae | https://finanshels.com/bookkeeping-services-uae | 301 redirect to pillar, then unpublish the page | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)

## Location pages (29)
# | Location page (thin/programmatic) | Recommended 301 to pillar | Status (24 Aug 2026)
1 | https://finanshels.com/locations/accounting-and-bookkeeping-services-in-dubai | https://finanshels.com/bookkeeping-services-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
2 | https://finanshels.com/locations/best-corporate-tax-filing-service-provider-in-the-abu-dhabi-trusted-by-dubai-startups-smes | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
3 | https://finanshels.com/locations/best-corporate-tax-filing-service-provider-in-the-ajman-trusted-by-dubai-startups-smes | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
4 | https://finanshels.com/locations/best-corporate-tax-filing-service-provider-in-the-dubai | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
5 | https://finanshels.com/locations/best-corporate-tax-filing-service-provider-in-the-sharjah-trusted-by-dubai-startups-smes | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
6 | https://finanshels.com/locations/best-corporate-tax-tool-in-dubai | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
7 | https://finanshels.com/locations/bookkeeping-services-in-abu-dhabi | https://finanshels.com/bookkeeping-services-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
8 | https://finanshels.com/locations/bookkeeping-services-in-ajman | https://finanshels.com/bookkeeping-services-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
9 | https://finanshels.com/locations/bookkeeping-services-in-sharjah | https://finanshels.com/bookkeeping-services-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
10 | https://finanshels.com/locations/corporate-tax-tool-dubai-creek | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
11 | https://finanshels.com/locations/corporate-tax-tool-in-abu-dhabi | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
12 | https://finanshels.com/locations/corporate-tax-tool-in-ajman | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
13 | https://finanshels.com/locations/corporate-tax-tool-in-burj-park | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
14 | https://finanshels.com/locations/corporate-tax-tool-in-deira | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
15 | https://finanshels.com/locations/corporate-tax-tool-in-downtown-dubai | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
16 | https://finanshels.com/locations/corporate-tax-tool-in-dubai-creek-harbor | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
17 | https://finanshels.com/locations/corporate-tax-tool-in-dubai-marina | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
18 | https://finanshels.com/locations/corporate-tax-tool-in-jumeirah-beach | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
19 | https://finanshels.com/locations/corporate-tax-tool-in-kite-beach | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
20 | https://finanshels.com/locations/corporate-tax-tool-in-marina-beach | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
21 | https://finanshels.com/locations/corporate-tax-tool-in-palm-jumeirah | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
22 | https://finanshels.com/locations/corporate-tax-tool-in-sharjah | https://finanshels.com/services/corporate-tax-return-filing-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
23 | https://finanshels.com/locations/vat-consultants-in-dubai | https://finanshels.com/services/vat-filing-and-accounting-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
24 | https://finanshels.com/locations/vat-registration-in-abu-dhabi | https://finanshels.com/services/vat-filing-and-accounting-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
25 | https://finanshels.com/locations/vat-registration-in-ajman | https://finanshels.com/services/vat-filing-and-accounting-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
26 | https://finanshels.com/locations/vat-registration-in-dubai | https://finanshels.com/services/vat-filing-and-accounting-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
27 | https://finanshels.com/locations/vat-registration-in-sharjah | https://finanshels.com/services/vat-filing-and-accounting-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
28 | https://finanshels.com/locations/vat-tool-in-abu-dhabi | https://finanshels.com/services/vat-filing-and-accounting-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)
29 | https://finanshels.com/locations/vat-tool-in-dubai | https://finanshels.com/services/vat-filing-and-accounting-in-uae | DONE - 301 live to pillar, page unpublished (verified 24 Aug 2026)

## Landing pages (44)
# | Landing page (paid - keep live) | Action | Status (24 Aug 2026)
1 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-arabic-page | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
2 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-at-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
3 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-at-finanshels-arabic-page | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
4 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-at-finanshels-desk | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
5 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-by-finanshels-uae | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
6 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-for-bahrain-businesses-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
7 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-for-bahrain-businesses-finanshels-desk | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
8 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-for-kuwait-businesses-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
9 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-for-kuwait-businesses-finanshels-desk | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
10 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-for-oman-businesses-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
11 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-for-oman-businesses-finanshels-desk | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
12 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-for-qatar-businesses-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
13 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-for-qatar-businesses-finanshels-desk | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
14 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-for-saudi-businesses-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
15 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-with-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
16 | https://finanshels.com/landing-pages/accounting-and-bookkeeping-service-with-finanshels-copy | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
17 | https://finanshels.com/landing-pages/accounting-firm-trusted-by-5000-uae-businesses | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
18 | https://finanshels.com/landing-pages/aml-compliance-filing-in-uae-with-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
19 | https://finanshels.com/landing-pages/aml-webinar | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
20 | https://finanshels.com/landing-pages/are-uae-realtors-really-prepared-for-increased-aml-scrutiny | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
21 | https://finanshels.com/landing-pages/audit-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
22 | https://finanshels.com/landing-pages/audits-by-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
23 | https://finanshels.com/landing-pages/bookkeeping-service-uae | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
24 | https://finanshels.com/landing-pages/claim-your-free-consultation | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
25 | https://finanshels.com/landing-pages/company-liquidation-services-in-uae-with-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
26 | https://finanshels.com/landing-pages/corporate-tax-filing-with-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
27 | https://finanshels.com/landing-pages/corporate-tax-filing-with-finanshels-bing | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
28 | https://finanshels.com/landing-pages/corporate-tax-registration-with-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
29 | https://finanshels.com/landing-pages/ct-filing-offer-for-dfhq-founders | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
30 | https://finanshels.com/landing-pages/filed-your-corporate-tax-return-think-twice | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
31 | https://finanshels.com/landing-pages/finanshels-corporate-tax-registration-in-the-uae | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
32 | https://finanshels.com/landing-pages/finanshels-top-choice-for-uae-businesses-looking-for-taxation-and-compliances | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
33 | https://finanshels.com/landing-pages/free-corporate-tax-registration-with-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
34 | https://finanshels.com/landing-pages/goaml-registration-services-in-uae | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
35 | https://finanshels.com/landing-pages/most-uae-founders-are-about-to-get-blindsided-by-their-own-invoices | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
36 | https://finanshels.com/landing-pages/online-taxes-and-bookkeeping-services-from-aed-199-in-the-uae | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
37 | https://finanshels.com/landing-pages/sef-attendee-offer | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
38 | https://finanshels.com/landing-pages/step-attendee-offer | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
39 | https://finanshels.com/landing-pages/tax-consultation-with-gautam | Add meta robots: noindex, nofollow (keep page live for ads) | BLOCKED - a redirect rule sends this URL to /landing-pages/free-financial-model-assessment which is 404. Page itself is published + noindexed. Fix: delete the redirect rule in Webflow Site Settings > Publishing > 301 Redirects (or publish the target page).
40 | https://finanshels.com/landing-pages/uaes-top-accountants-handle-your-books | Add meta robots: noindex, nofollow (keep page live for ads) | STAGED - noindex toggle already live; the 'noindex, nofollow' custom head tag was added 24 Aug and goes live on the next site publish.
41 | https://finanshels.com/landing-pages/vat-filing-for-your-business-desk | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
42 | https://finanshels.com/landing-pages/vat-filing-services-for-your-business | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
43 | https://finanshels.com/landing-pages/vat-registration-service-in-uae | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)
44 | https://finanshels.com/landing-pages/vat-registration-with-finanshels | Add meta robots: noindex, nofollow (keep page live for ads) | DONE - live (HTTP 200), noindex + nofollow meta present (verified 24 Aug 2026)

## Tasks summary
Task | Mechanism | Notes | Status (24 Aug 2026)
Industry & location page redirects | Webflow > Site Settings > Publishing > 301 Redirects | Add old path > pillar path. Then unpublish the old page. | DONE - all 34 redirect rules live, all 34 pages set to draft. Verified by live HTTP checks: 34/34 single-hop 301s to the correct pillar.
Noindex the 44 paid landing pages | Per page: Settings > 'Disable search-engine indexing' + noindex,nofollow custom head code | robots.txt does NOT noindex - it only blocks crawl. Use the meta robots tag. | DONE (43/44 verified live; 1 staged) - see Landing pages tab rows 39-40 for the two exceptions.
Do NOT block landing pages in robots.txt | - | If you both noindex AND robots.txt-disallow, Google can't read the noindex tag. | VERIFIED - robots.txt does not disallow /landing-pages/; pages remain crawlable so noindex is readable.
Optional supporting step | Remove paid landing pages from sitemap | Reduces discovery, but is NOT a substitute for the noindex meta tag. | NO ACTION NEEDED - sitemap.xml (751 URLs) already contains zero /landing-pages/, /locations/, or pruned /services/ URLs.